## 1. Phase 2 - Agentic Voice Task
Tasks | Assigned To | % Allocation | Start Date | End Date | Duration | Predecessors | Description | Notes | Baseline Start | Baseline Finish | Variance
Development Phase | [8 empty] | 2025-11-05 | 2025-12-12 | -2d
FPS Draft Proposal | FPS |  | 2025-11-05 | 2025-11-05 | 1d |  |  |  | 2025-11-05 | 2025-11-05 | 0
FPS Final Proposal (SOW) | FPS |  | 2025-11-20 | 2025-11-20 | 1d |  |  |  | 2025-11-20 | 2025-11-20 | 0
Frontier SOW Approval | Frontier |  | 2025-11-21 | 2025-11-21 | 1d | 5 |  |  | 2025-11-21 | 2025-11-21 | 0
Frontier Staging Dependencies Complete | Frontier IT / Cloud |  | 2025-11-21 | 2025-11-21 | 1d |  |  |  | 2025-11-21 | 2025-11-21 | 0
Cognigy Staging Dependencies Phase 1 | Cognigy |  | 2025-12-01 | 2025-12-01 | 1d |  |  |  | 2025-12-01 | 2025-12-01 | 0
Cognigy Staging Dependencies Phase 2 | Cognigy |  | 2025-12-08 | 2025-12-08 | 1d |  |  |  | 2025-12-08 | 2025-12-08 | 0
IGT Staging Dependencies Complete | IGT |  | 2025-12-08 | 2025-12-26 | 14d |  |  |  | 2025-12-08 | 2025-12-08 | -13d
FPS Development - Knowledgebase | FPS |  | 2025-11-21 | 2025-12-11 | 13d |  |  |  | 2025-12-08 | 2025-12-08 | -3d
Frontier Production Dependencies Complete | Frontier IT |  | 2025-12-01 | 2025-12-08 | 6d |  |  |  | 2025-12-08 | 2025-12-08 | 0
FPS Development - Partner Integrations | FPS |  | 2025-12-10 | 2025-12-22 | 9d |  |  |  | 2025-12-12 | 2025-12-12 | -6d
QA & Testing Phase
FPS QA Testing | FPS |  | 2025-12-11 | 2025-12-22 | 8d |  |  |  | 2025-12-08 | 2025-12-12 | -6d
CSG Staging Dependencies Complete | CSG |  | 2025-12-23 | 2025-12-23 | 1d | 37 |  |  | 2025-12-15 | 2025-12-15 | -6d
Cognigy Production Dependencies Complete | Cognigy |  | 2025-12-11 | 2025-12-22 | 8d |  |  |  | 2025-12-15 | 2025-12-15 | -5d
IGT Production Dependencies Complete | IGT |  | 2025-12-22 | 2025-12-31 | 7d |  |  | This is the estimate date as we are not sure by when can we expect to get the production readiness | 2025-12-15 | 2025-12-15 | -11d
Frontier UAT Testing | Frontier |  | 2025-12-22 | 2026-01-01 | 8d |  |  |  | 2025-12-15 | 2025-12-19 | -8d
CSG Production Dependencies Complete | CSG |  | 2025-12-22 | 2025-12-31 | 7d |  |  |  | 2025-12-17 | 2025-12-17 | -9d
Frontier UAT Approval | Frontier |  | 2026-01-02 | 2026-01-02 | 1d |  |  |  | 2025-12-19 | 2025-12-19 | -9d
Production Deployment |  |  | 2025-12-22 | 2026-01-13 | 16d |  |  |  | 2025-12-22 | 2026-01-07 | -4d
Frontier Production Dependencies Complete | Frontier Cloud |  | 2025-12-22 | 2026-01-02 | 9d |  |  | CSG routing config, AB testing, IGT, Cognigy | 2025-12-22 | 2026-01-05 | 1d
Frontier Production Go-Live Approval (CAB) | Frontier CAB |  | 2026-01-05 | 2026-01-08 | 4d |  |  |  | 2026-01-05 | 2026-01-06 | -2d
FPS Production Deployment | FPS |  | 2026-01-13 | 2026-01-13 | 1d |  |  |  | 2026-01-07 | 2026-01-07 | -4d

## Comments
Row 1 | @chirag.handa@fpsinc.com - Please review and let me know if you have any questions. | Scott Turner | 11/26/25 3:49 PM
Row 19 | as per update on 5th Dec by Sandeep (IGT) | Chirag Handa | 12/05/25 12:38 PM
Row 19 | End date for IGT Staging Dependencies Complete changed to December 26th | Chirag Handa | 12/05/25 10:54 AM
Sheet | @andrew.shaw@fpsinc.com | Scott Turner | 11/26/25 3:51 PM
Sheet | @chirag.handa@fpsinc.com - I have renamed the original "Notes" column as "Description" and added a new column titled "Notes". Please let me know if this gets you what you were needing. | Scott Turner | 11/26/25 3:50 PM