## Executive Summary
PHASE 2 AGENTIC VOICE - SCHEDULE CORRECTION PLAN
Generated: | 2025-12-09 17:49:02
TARGET GO-LIVE (APPROVED): | January 13, 2026
ORIGINAL BASELINE: | January 7, 2026
CURRENT PROJECTION: | January 30, 2026
RECALCULATED PROJECTION: | January 16, 2026
ROOT CAUSES:
1. FPS Developer Reassignment | Nov 25 - Dec 9 (4 working day shift approved)
2. IGT SIP Trunks Delay | Dec 8 -> Dec 23 (2-3 weeks vs 1 week)
CRITICAL PATH RECALCULATION:
IGT Staging Complete | Dec 23 (was Dec 8) +15 days
FPS QA Testing Complete | Jan 5 (was Dec 12) +24 days
Frontier UAT Complete | Jan 12 (was Dec 19) +24 days
UAT Approval | Jan 13 (was Dec 19) +25 days
CAB Approval | Jan 15 (was Jan 6) +9 days
Production Go-Live | Jan 16 (was Jan 7) +9 days
GAP TO TARGET: | 3 days (Jan 16 vs Jan 13)
COMPRESSION OPTIONS:
Option A: Compress UAT 5d -> 3d | Saves 2 days
Option B: Compress CAB 2d -> 1d | Saves 1 day
Option C: Parallel UAT/QA overlap | Saves 1-2 days
BASELINE UPDATES REQUIRED: | 54 tasks
TASKS BLOCKED BY IGT: | 22 tasks
COMPLETED TASKS (no change): | 21 tasks

## Baseline Updates
Row | Task Name | Assigned To | Status | Current Baseline | New Baseline | Action | Notes
17 | Cognigy Staging Dependencies Phase 2 | Cognigy | In Progress | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target) | Blocked by IGT Row 24 (SIP Trunks)
19 | Connect SIP trunks | Cognigy | Not Started | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target) | Blocked by IGT Row 24 (SIP Trunks)
20 | Assign numbers | Cognigy | Not Started | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target) | Blocked by IGT Row 24 (SIP Trunks)
21 | Create SIP flow | Cognigy | Not Started | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target) | Blocked by IGT Row 24 (SIP Trunks)
22 | IGT Staging Dependencies Complete | IGT | Not Started | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target)
23 | Configure 800 number for SIP REFER for CSG Lookup | IGT | Not Started | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target)
24 | Set up SIP trunks via NICE CXone | IGT | Not Started | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target)
25 | Configure the Signal API | IGT | Not Started | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target)
26 | Complete queue mapping | IGT | Not Started | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target)
27 | Provision 8 DID test numbers | IGT | Not Started | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target)
28 | FPS Development - Knowledgebase | FPS | In Progress | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target)
32 | Tune LLM responses for accuracy and clarity | FPS | In Progress | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target)
33 | Frontier Production Dependencies Complete | Frontier | In Progress | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target)
34 | Secure Architecture Review Board (ARB) approval | Frontier | In Progress | 2025-12-08 | 2025-12-14 | PROPORTIONAL SHIFT (30d before target)
36 | FPS Development - Partner Integrations | FPS | Not Started | 2025-12-12 | 2025-12-18 | PROPORTIONAL SHIFT (26d before target)
37 | Implement required partner API integrations | FPS | Not Started | 2025-12-12 | 2025-12-18 | PROPORTIONAL SHIFT (26d before target) | Blocked by IGT Row 24 (SIP Trunks)
38 | Set up the necessary data exchange endpoints | FPS | Not Started | 2025-12-12 | 2025-12-18 | PROPORTIONAL SHIFT (26d before target) | Blocked by IGT Row 24 (SIP Trunks)
39 | QA & Testing Phase |  | Not Started | 2025-12-19 | 2025-12-25 | PROPORTIONAL SHIFT (19d before target)
40 | FPS QA Testing | FPS | Not Started | 2025-12-12 | 2025-12-18 | PROPORTIONAL SHIFT (26d before target) | Blocked by IGT Row 24 (SIP Trunks)
41 | Execute the full end-to-end Agentic Voice test pla | FPS | Not Started | 2025-12-12 | 2025-12-18 | PROPORTIONAL SHIFT (26d before target) | Blocked by IGT Row 24 (SIP Trunks)
42 | Perform all testing within the QA environment | FPS | Not Started | 2025-12-12 | 2025-12-18 | PROPORTIONAL SHIFT (26d before target) | Blocked by IGT Row 24 (SIP Trunks)
43 | CSG Staging Dependencies Complete (Testing) | CSG | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target)
44 | Configure IVR call routing using SIP REFER to IGT | CSG | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target)
45 | Set up the 800 test number for the direct_AI Engli | CSG | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target)
46 | Cognigy Production Dependencies Complete | Cognigy | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target) | Blocked by IGT Row 24 (SIP Trunks)
47 | Provision the Production 800 number | Cognigy | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target) | Blocked by IGT Row 24 (SIP Trunks)
48 | Set up SIP trunks to Cognigy | Cognigy | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target) | Blocked by IGT Row 24 (SIP Trunks)
49 | Configure the Signal API | Cognigy | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target) | Blocked by IGT Row 24 (SIP Trunks)
50 | Provision 2 DID test numbers | Cognigy | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target) | Blocked by IGT Row 24 (SIP Trunks)
51 | IGT Production Dependencies Complete | IGT | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target) | Blocked by IGT Row 24 (SIP Trunks)
52 | Provision the 800 number for production | IGT | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target) | Blocked by IGT Row 24 (SIP Trunks)
53 | Set up SIP trunks to Cognigy | IGT | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target) | Blocked by IGT Row 24 (SIP Trunks)
54 | Configure the Signal API | IGT | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target) | Blocked by IGT Row 24 (SIP Trunks)
55 | Provision 2 DID test numbers | IGT | Not Started | 2025-12-15 | 2025-12-21 | PROPORTIONAL SHIFT (23d before target) | Blocked by IGT Row 24 (SIP Trunks)
56 | Frontier UAT Testing | Frontier | Not Started | 2025-12-19 | 2025-12-25 | PROPORTIONAL SHIFT (19d before target) | Indirect IGT dependency via Row 40
57 | Execute the full end-to-end Agentic Voice test pla | Frontier | Not Started | 2025-12-19 | 2025-12-25 | PROPORTIONAL SHIFT (19d before target) | Indirect IGT dependency via Row 40
58 | Perform all testing within the UAT environment | Frontier | Not Started | 2025-12-19 | 2025-12-25 | PROPORTIONAL SHIFT (19d before target) | Indirect IGT dependency via Row 40
59 | CSG Production Dependencies Complete (UAT Approval | CSG | In Progress | 2025-12-17 | 2025-12-23 | PROPORTIONAL SHIFT (21d before target)
60 | Configure Production IVR call routing using SIP RE | CSG | In Progress | 2025-12-17 | 2025-12-23 | PROPORTIONAL SHIFT (21d before target)
61 | Set the routing percentage for “Unknown” call type | CSG | In Progress | 2025-12-17 | 2025-12-23 | PROPORTIONAL SHIFT (21d before target)
62 | Frontier UAT Approval | Frontier | Not Started | 2025-12-19 | 2025-12-25 | PROPORTIONAL SHIFT (19d before target)
63 | Obtain formal UAT sign-off | Frontier | Not Started | 2025-12-19 | 2025-12-25 | PROPORTIONAL SHIFT (19d before target)
64 | Production Deployment |  | Not Started | 2026-01-07 | 2026-01-13 | SHIFT +6d (Jan 7 -> Jan 13)
65 | Frontier Production Dependencies Complete | Frontier | In Progress | 2026-01-05 | 2026-01-11 | PROPORTIONAL SHIFT (2d before target)
66 | Provision Production Azure AI Speech STT keys | Frontier | In Progress | 2026-01-05 | 2026-01-11 | PROPORTIONAL SHIFT (2d before target)
67 | Provision Production Azure AI Speech TTS keys | Frontier | In Progress | 2026-01-05 | 2026-01-11 | PROPORTIONAL SHIFT (2d before target)
68 | Set up Production OpenAI LLM credentials | Frontier | Not Started | 2026-01-05 | 2026-01-11 | PROPORTIONAL SHIFT (2d before target)
69 | Frontier Production Go-Live Approval (CAB) | Frontier | Not Started | 2026-01-06 | 2026-01-12 | PROPORTIONAL SHIFT (1d before target)
70 | Present the deployment plan to the Change Advisory | Frontier | Not Started | 2026-01-06 | 2026-01-12 | PROPORTIONAL SHIFT (1d before target)
71 | Secure final approval for the Production Go-Live | Frontier | Not Started | 2026-01-06 | 2026-01-12 | PROPORTIONAL SHIFT (1d before target)
72 | FPS Production Deployment | FPS | Not Started | 2026-01-07 | 2026-01-13 | SHIFT +6d (Jan 7 -> Jan 13)
73 | Deploy the solution to Production | FPS | Not Started | 2026-01-07 | 2026-01-13 | SHIFT +6d (Jan 7 -> Jan 13)
74 | Perform sanity testing to confirm core functionali | FPS | Not Started | 2026-01-07 | 2026-01-13 | SHIFT +6d (Jan 7 -> Jan 13)
75 | Initiate post-launch monitoring to ensure stabilit | FPS | Not Started | 2026-01-07 | 2026-01-13 | SHIFT +6d (Jan 7 -> Jan 13)

## IGT Blocked Tasks
Row | Task Name | Assigned To | Predecessor | Current End | Recalc End | Slip Days
17 | Cognigy Staging Dependencies Phase 2 | Cognigy | 24FS +1d | 2025-12-30 | Recalc from Dec 23
19 | Connect SIP trunks | Cognigy | 24FS +1d | 2025-12-30 | Recalc from Dec 23
20 | Assign numbers | Cognigy | 24FS +1d | 2025-12-30 | Recalc from Dec 23
21 | Create SIP flow | Cognigy | 24FS +1d | 2025-12-30 | Recalc from Dec 23
37 | Implement required partner API integrations | FPS | 24FS +1d | 2026-01-07 | Recalc from Dec 23
38 | Set up the necessary data exchange endpoints | FPS | 24FS +1d | 2026-01-07 | Recalc from Dec 23
40 | FPS QA Testing | FPS | 24FS +1d | 2026-01-06 | Recalc from Dec 23
41 | Execute the full end-to-end Agentic Voice tes | FPS | 24FS +1d | 2026-01-06 | Recalc from Dec 23
42 | Perform all testing within the QA environment | FPS | 24FS +1d | 2026-01-06 | Recalc from Dec 23
46 | Cognigy Production Dependencies Complete | Cognigy | 24FS +1d | 2026-01-06 | Recalc from Dec 23
47 | Provision the Production 800 number | Cognigy | 24FS +1d | 2026-01-06 | Recalc from Dec 23
48 | Set up SIP trunks to Cognigy | Cognigy | 24FS +1d | 2026-01-06 | Recalc from Dec 23
49 | Configure the Signal API | Cognigy | 24FS +1d | 2026-01-06 | Recalc from Dec 23
50 | Provision 2 DID test numbers | Cognigy | 24FS +1d | 2026-01-06 | Recalc from Dec 23
51 | IGT Production Dependencies Complete | IGT | 24FS +1d | 2026-01-07 | Recalc from Dec 23
52 | Provision the 800 number for production | IGT | 24FS +1d | 2026-01-07 | Recalc from Dec 23
53 | Set up SIP trunks to Cognigy | IGT | 24FS +1d | 2026-01-07 | Recalc from Dec 23
54 | Configure the Signal API | IGT | 24FS +1d | 2026-01-07 | Recalc from Dec 23
55 | Provision 2 DID test numbers | IGT | 24FS +1d | 2026-01-07 | Recalc from Dec 23
56 | Frontier UAT Testing | Frontier | 40FS +1d | 2026-01-19 | Recalc from Dec 23
57 | Execute the full end-to-end Agentic Voice tes | Frontier | 40FS +1d | 2026-01-19 | Recalc from Dec 23
58 | Perform all testing within the UAT environmen | Frontier | 40FS +1d | 2026-01-19 | Recalc from Dec 23

## Full Schedule
Row | Task | Assigned | Status | Health | Duration | Current Start | Current End | Current Baseline | New Baseline | Variance | Predecessor | Notes
1 | Development Phase |  | Complete | Green | 43d | 2025-11-05 | 2026-01-07 | 2025-12-12 |  | 0.04
2 | FPS Draft Proposal | FPS | Complete | Green | 2d | 2025-11-05 | 2025-11-06 | 2025-11-05 |  | 0
3 | Draft the initial proposal for the Agentic Voice p | FPS | Complete | Green | 1d | 2025-11-05 | 2025-11-05 | 2025-11-05 |  | 0
4 | Submit the proposal for stakeholder review | FPS | Complete | Green | 1d | 2025-11-06 | 2025-11-06 | 2025-11-05 |  | -1 | 3FS
5 | FPS Final Proposal (SOW) | FPS | Complete | Green | 1d | 2025-11-07 | 2025-11-07 | 2025-11-20 |  | 1 | 2FS
6 | Finalize the Statement of Work (SOW) contract | FPS | Complete | Green | 1d | 2025-11-07 | 2025-11-07 | 2025-11-20 |  | 13
7 | Submit the SOW for signature | FPS | Complete | Green | 1d | 2025-11-07 | 2025-11-07 | 2025-11-20 |  | 13
8 | Frontier SOW Approval | Frontier | Complete | Green | 1d | 2025-11-10 | 2025-11-10 | 2025-11-21 |  | 1 | 5FS
9 | Obtain formal approval on the Statement of Work (S | Frontier | Complete | Green | 1d | 2025-11-10 | 2025-11-10 | 2025-11-21 |  | 11
10 | Frontier Staging Dependencies Complete | Frontier | Complete | Green | 1d | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | 0
11 | Provision KnowledgeOwl APIs for the Staging enviro | Frontier | Complete | Green | 1d | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | 0
12 | Generate and configure the OpenAI LLM (gpt-4o-mini | Frontier | Complete | Green | 1d | 2025-11-21 | 2025-11-21 | 2025-11-21 |  | 0
13 | Cognigy Staging Dependencies Phase 1 | Cognigy | Complete | Green | 1d | 2025-12-01 | 2025-12-01 | 2025-12-01 |  | 0
14 | Activate and validate VoiceGateway licenses | Cognigy | Complete | Green | 1d | 2025-12-01 | 2025-12-01 | 2025-12-01 |  | 0
15 | Deliver and validate Azure STT/TTS | Cognigy | Complete | Green | 1d | 2025-12-01 | 2025-12-01 | 2025-12-01 |  | 0
16 | Provide voice-focused Cognigy templates | Cognigy | Complete | Green | 1d | 2025-12-01 | 2025-12-01 | 2025-12-01 |  | 0
17 | Cognigy Staging Dependencies Phase 2 | Cognigy | In Progress | Green | 3d | 2025-12-26 | 2025-12-30 | 2025-12-08 | 2025-12-14 | 0 | 24FS +1d
18 | Provision VoiceGateway | Cognigy | Complete | Green | 3d | 2025-12-26 | 2025-12-30 | 2025-12-08 |  | -22 | 24FS +1d
19 | Connect SIP trunks | Cognigy | Not Started | Red | 3d | 2025-12-26 | 2025-12-30 | 2025-12-08 | 2025-12-14 | -22 | 24FS +1d
20 | Assign numbers | Cognigy | Not Started | Red | 3d | 2025-12-26 | 2025-12-30 | 2025-12-08 | 2025-12-14 | -22 | 24FS +1d
21 | Create SIP flow | Cognigy | Not Started | Red | 3d | 2025-12-26 | 2025-12-30 | 2025-12-08 | 2025-12-14 | -22 | 24FS +1d
22 | IGT Staging Dependencies Complete | IGT | Not Started | Yellow | 12d | 2025-12-08 | 2025-12-23 | 2025-12-08 | 2025-12-14 | 0
23 | Configure 800 number for SIP REFER for CSG Lookup | IGT | Not Started | Red | 12d | 2025-12-08 | 2025-12-23 | 2025-12-08 | 2025-12-14 | -15
24 | Set up SIP trunks via NICE CXone | IGT | Not Started | Red | 12d | 2025-12-08 | 2025-12-23 | 2025-12-08 | 2025-12-14 | -15
25 | Configure the Signal API | IGT | Not Started | Red | 12d | 2025-12-08 | 2025-12-23 | 2025-12-08 | 2025-12-14 | -15 |  | 12/05 - Sandeep (IGT) mentioned the configuration will take another 2–3 weeks, which means we can target December 23rd for completion.
26 | Complete queue mapping | IGT | Not Started | Red | 12d | 2025-12-08 | 2025-12-23 | 2025-12-08 | 2025-12-14 | -15
27 | Provision 8 DID test numbers | IGT | Not Started | Red | 12d | 2025-12-08 | 2025-12-23 | 2025-12-08 | 2025-12-14 | -15
28 | FPS Development - Knowledgebase | FPS | In Progress | Yellow | 13d | 2025-11-21 | 2025-12-11 | 2025-12-08 | 2025-12-14 | 0
29 | Validate the KnowledgeOwl API | FPS | Complete | Green | 13d | 2025-11-21 | 2025-12-11 | 2025-12-08 |  | -3
30 | Optimize FAQ lookup specifically for voice interac | FPS | Complete | Green | 13d | 2025-11-21 | 2025-12-11 | 2025-12-08 |  | -3 |  | -12/09 - Completed; accuracy enhancements in progress.
31 | Implement fallback logic for unanswered or unclear | FPS | Complete | Green | 13d | 2025-11-21 | 2025-12-11 | 2025-12-08 |  | -3
32 | Tune LLM responses for accuracy and clarity | FPS | In Progress | Yellow | 13d | 2025-11-21 | 2025-12-11 | 2025-12-08 | 2025-12-14 | -3
33 | Frontier Production Dependencies Complete | Frontier | In Progress | Green | 14d | 2025-12-01 | 2025-12-18 | 2025-12-08 | 2025-12-14 | 0
34 | Secure Architecture Review Board (ARB) approval | Frontier | In Progress | Green | 14d | 2025-12-01 | 2025-12-18 | 2025-12-08 | 2025-12-14 | 0
35 | Validate Production KnowledgeOwl APIs | Frontier | Complete | Green | 6d | 2025-12-01 | 2025-12-08 | 2025-12-08 |  | 0
36 | FPS Development - Partner Integrations | FPS | Not Started | Green | 9d | 2025-12-26 | 2026-01-07 | 2025-12-12 | 2025-12-18 | 0
37 | Implement required partner API integrations | FPS | Not Started | Red | 9d | 2025-12-26 | 2026-01-07 | 2025-12-12 | 2025-12-18 | -26 | 24FS +1d
38 | Set up the necessary data exchange endpoints | FPS | Not Started | Red | 9d | 2025-12-26 | 2026-01-07 | 2025-12-12 | 2025-12-18 | -26 | 24FS +1d
39 | QA & Testing Phase |  | Not Started | Yellow | 32d | 2025-12-08 | 2026-01-21 | 2025-12-19 | 2025-12-25 | 0.11
40 | FPS QA Testing | FPS | Not Started | Green | 8d | 2025-12-26 | 2026-01-06 | 2025-12-12 | 2025-12-18 | 0 | 24FS +1d
41 | Execute the full end-to-end Agentic Voice test pla | FPS | Not Started | Red | 8d | 2025-12-26 | 2026-01-06 | 2025-12-12 | 2025-12-18 | -25 | 24FS +1d
42 | Perform all testing within the QA environment | FPS | Not Started | Red | 8d | 2025-12-26 | 2026-01-06 | 2025-12-12 | 2025-12-18 | -25 | 24FS +1d
43 | CSG Staging Dependencies Complete (Testing) | CSG | Not Started | Yellow | 5d | 2025-12-08 | 2025-12-12 | 2025-12-15 | 2025-12-21 | 1
44 | Configure IVR call routing using SIP REFER to IGT | CSG | Not Started | Yellow | 5d | 2025-12-08 | 2025-12-12 | 2025-12-15 | 2025-12-21 | 3
45 | Set up the 800 test number for the direct_AI Engli | CSG | Not Started | Yellow | 5d | 2025-12-08 | 2025-12-12 | 2025-12-15 | 2025-12-21 | 3
46 | Cognigy Production Dependencies Complete | Cognigy | Not Started | Green | 8d | 2025-12-26 | 2026-01-06 | 2025-12-15 | 2025-12-21 | 0 | 24FS +1d
47 | Provision the Production 800 number | Cognigy | Not Started | Red | 8d | 2025-12-26 | 2026-01-06 | 2025-12-15 | 2025-12-21 | -22 | 24FS +1d
48 | Set up SIP trunks to Cognigy | Cognigy | Not Started | Red | 8d | 2025-12-26 | 2026-01-06 | 2025-12-15 | 2025-12-21 | -22 | 24FS +1d
49 | Configure the Signal API | Cognigy | Not Started | Red | 8d | 2025-12-26 | 2026-01-06 | 2025-12-15 | 2025-12-21 | -22 | 24FS +1d
50 | Provision 2 DID test numbers | Cognigy | Not Started | Red | 8d | 2025-12-26 | 2026-01-06 | 2025-12-15 | 2025-12-21 | -22 | 24FS +1d
51 | IGT Production Dependencies Complete | IGT | Not Started | Green | 9d | 2025-12-26 | 2026-01-07 | 2025-12-15 | 2025-12-21 | 0 | 24FS +1d
52 | Provision the 800 number for production | IGT | Not Started | Red | 9d | 2025-12-26 | 2026-01-07 | 2025-12-15 | 2025-12-21 | -23 | 24FS +1d
53 | Set up SIP trunks to Cognigy | IGT | Not Started | Red | 9d | 2025-12-26 | 2026-01-07 | 2025-12-15 | 2025-12-21 | -23 | 24FS +1d
54 | Configure the Signal API | IGT | Not Started | Red | 9d | 2025-12-26 | 2026-01-07 | 2025-12-15 | 2025-12-21 | -23 | 24FS +1d
55 | Provision 2 DID test numbers | IGT | Not Started | Red | 9d | 2025-12-26 | 2026-01-07 | 2025-12-15 | 2025-12-21 | -23 | 24FS +1d
56 | Frontier UAT Testing | Frontier | Not Started | Green | 8d | 2026-01-08 | 2026-01-19 | 2025-12-19 | 2025-12-25 | 0 | 40FS +1d
57 | Execute the full end-to-end Agentic Voice test pla | Frontier | Not Started | Red | 8d | 2026-01-08 | 2026-01-19 | 2025-12-19 | 2025-12-25 | -31 | 40FS +1d
58 | Perform all testing within the UAT environment | Frontier | Not Started | Red | 8d | 2026-01-08 | 2026-01-19 | 2025-12-19 | 2025-12-25 | -31 | 40FS +1d
59 | CSG Production Dependencies Complete (UAT Approval | CSG | In Progress | Green | 6d | 2025-12-12 | 2025-12-19 | 2025-12-17 | 2025-12-23 | 0
60 | Configure Production IVR call routing using SIP RE | CSG | In Progress | Yellow | 6d | 2025-12-12 | 2025-12-19 | 2025-12-17 | 2025-12-23 | -2
61 | Set the routing percentage for “Unknown” call type | CSG | In Progress | Yellow | 6d | 2025-12-12 | 2025-12-19 | 2025-12-17 | 2025-12-23 | -2
62 | Frontier UAT Approval | Frontier | Not Started | Green | 1d | 2026-01-21 | 2026-01-21 | 2025-12-19 | 2025-12-25 | 0 | 56FS +1d
63 | Obtain formal UAT sign-off | Frontier | Not Started | Red | 1d | 2026-01-21 | 2026-01-21 | 2025-12-19 | 2025-12-25 | -33 | 56FS +1d
64 | Production Deployment |  | Not Started | Green | 30d | 2025-12-19 | 2026-01-30 | 2026-01-07 | 2026-01-13 | 0 | 34FS
65 | Frontier Production Dependencies Complete | Frontier | In Progress | Green | 9d | 2025-12-19 | 2026-01-01 | 2026-01-05 | 2026-01-11 | 0 | 34FS
66 | Provision Production Azure AI Speech STT keys | Frontier | In Progress | Red | 9d | 2025-12-19 | 2026-01-01 | 2026-01-05 | 2026-01-11 | -30 | 34FS
67 | Provision Production Azure AI Speech TTS keys | Frontier | In Progress | Red | 9d | 2025-12-19 | 2026-01-01 | 2026-01-05 | 2026-01-11 | -30 | 34FS
68 | Set up Production OpenAI LLM credentials | Frontier | Not Started | Red | 9d | 2025-12-19 | 2026-01-01 | 2026-01-05 | 2026-01-11 | -30 | 34FS
69 | Frontier Production Go-Live Approval (CAB) | Frontier | Not Started | Green | 4d | 2026-01-23 | 2026-01-28 | 2026-01-06 | 2026-01-12 | 0 | 62FS +1d
70 | Present the deployment plan to the Change Advisory | Frontier | Not Started | Red | 4d | 2026-01-23 | 2026-01-28 | 2026-01-06 | 2026-01-12 | -22 | 62FS +1d
71 | Secure final approval for the Production Go-Live | Frontier | Not Started | Red | 4d | 2026-01-23 | 2026-01-28 | 2026-01-06 | 2026-01-12 | -22 | 62FS +1d
72 | FPS Production Deployment | FPS | Not Started | Green | 1d | 2026-01-30 | 2026-01-30 | 2026-01-07 | 2026-01-13 | 0 | 69FS +1d
73 | Deploy the solution to Production | FPS | Not Started | Red | 1d | 2026-01-30 | 2026-01-30 | 2026-01-07 | 2026-01-13 | -23 | 69FS +1d
74 | Perform sanity testing to confirm core functionali | FPS | Not Started | Red | 1d | 2026-01-30 | 2026-01-30 | 2026-01-07 | 2026-01-13 | -23 | 69FS +1d
75 | Initiate post-launch monitoring to ensure stabilit | FPS | Not Started | Red | 1d | 2026-01-30 | 2026-01-30 | 2026-01-07 | 2026-01-13 | -23 | 69FS +1d

## Update Instructions
SMARTSHEET UPDATE INSTRUCTIONS
STEP 1: BACKUP THE SHEET
- Export current sheet to Excel as backup
- Save with date stamp (e.g., Phase2_Backup_20251209.xlsx)
STEP 2: UPDATE BASELINES
Option A: Manual Update
- Open 'Baseline Updates' tab in this file
- For each row, update Baseline Finish to the New Baseline value
- Update Baseline Start if shown
Option B: API Update
- Run: python smartsheet_update_jan13.py
- Set SHEET_ID in the script first
- Set SMARTSHEET_ACCESS_TOKEN environment variable
STEP 3: VERIFY CRITICAL PATH
- Check Row 24 (IGT SIP Trunks) shows Dec 23 end date
- Verify dependent tasks cascade correctly from Dec 23
- Confirm FPS QA -> Frontier UAT -> CAB chain is correct
STEP 4: ADD NOTES
Row 25 (IGT Signal API): | Already has 12/05 note about delay
Row 28 (FPS Knowledgebase): | Add: Developer reassigned Nov 25 - Dec 9
Row 64 (Production Deployment): | Add: Baseline updated to Jan 13 per approval
STEP 5: RECALCULATE
- Smartsheet should auto-recalculate variance
- Health indicators will update
- Verify final Production Deployment date
EXPECTED RESULTS:
- Variance will show against Jan 13 baseline
- Production Deployment projection: ~Jan 16
- Gap to target: 3 days