## Corrections Plan
Row | Task | Assigned To | Status | Health | Current End | Current Baseline Finish | Current Variance | Baseline Action | New Baseline Finish | Current Predecessor | Predecessor Action | Schedule Action | Notes
1 | Development Phase |  | Complete | Green | 2026-01-07 | 2025-12-12 | 0.04 | PROPORTIONAL SHIFT | 2025-12-18
2 | FPS Draft Proposal | FPS | Complete | Green | 2025-11-06 | 2025-11-05 | 0 | PROPORTIONAL SHIFT | 2025-11-11
3 | Draft the initial proposal for the Agentic Voice p | FPS | Complete | Green | 2025-11-05 | 2025-11-05 | 0 | PROPORTIONAL SHIFT | 2025-11-11
4 | Submit the proposal for stakeholder review | FPS | Complete | Green | 2025-11-06 | 2025-11-05 | -1 | PROPORTIONAL SHIFT | 2025-11-11 | 3FS
5 | FPS Final Proposal (SOW) | FPS | Complete | Green | 2025-11-07 | 2025-11-20 | 1 | PROPORTIONAL SHIFT | 2025-11-26 | 2FS
6 | Finalize the Statement of Work (SOW) contract | FPS | Complete | Green | 2025-11-07 | 2025-11-20 | 13 | PROPORTIONAL SHIFT | 2025-11-26
7 | Submit the SOW for signature | FPS | Complete | Green | 2025-11-07 | 2025-11-20 | 13 | PROPORTIONAL SHIFT | 2025-11-26
8 | Frontier SOW Approval | Frontier | Complete | Green | 2025-11-10 | 2025-11-21 | 1 | PROPORTIONAL SHIFT | 2025-11-27 | 5FS
9 | Obtain formal approval on the Statement of Work (S | Frontier | Complete | Green | 2025-11-10 | 2025-11-21 | 11 | PROPORTIONAL SHIFT | 2025-11-27
10 | Frontier Staging Dependencies Complete | Frontier | Complete | Green | 2025-11-21 | 2025-11-21 | 0 | PROPORTIONAL SHIFT | 2025-11-27
11 | Provision KnowledgeOwl APIs for the Staging enviro | Frontier | Complete | Green | 2025-11-21 | 2025-11-21 | 0 | PROPORTIONAL SHIFT | 2025-11-27
12 | Generate and configure the OpenAI LLM (gpt-4o-mini | Frontier | Complete | Green | 2025-11-21 | 2025-11-21 | 0 | PROPORTIONAL SHIFT | 2025-11-27
13 | Cognigy Staging Dependencies Phase 1 | Cognigy | Complete | Green | 2025-12-01 | 2025-12-01 | 0 | PROPORTIONAL SHIFT | 2025-12-07
14 | Activate and validate VoiceGateway licenses | Cognigy | Complete | Green | 2025-12-01 | 2025-12-01 | 0 | PROPORTIONAL SHIFT | 2025-12-07
15 | Deliver and validate Azure STT/TTS | Cognigy | Complete | Green | 2025-12-01 | 2025-12-01 | 0 | PROPORTIONAL SHIFT | 2025-12-07
16 | Provide voice-focused Cognigy templates | Cognigy | Complete | Green | 2025-12-01 | 2025-12-01 | 0 | PROPORTIONAL SHIFT | 2025-12-07
17 | Cognigy Staging Dependencies Phase 2 | Cognigy | In Progress | Green | 2025-12-30 | 2025-12-08 | 0 | PROPORTIONAL SHIFT | 2025-12-14 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
18 | Provision VoiceGateway | Cognigy | Complete | Green | 2025-12-30 | 2025-12-08 | -22 | PROPORTIONAL SHIFT | 2025-12-14 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
19 | Connect SIP trunks | Cognigy | Not Started | Red | 2025-12-30 | 2025-12-08 | -22 | PROPORTIONAL SHIFT | 2025-12-14 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
20 | Assign numbers | Cognigy | Not Started | Red | 2025-12-30 | 2025-12-08 | -22 | PROPORTIONAL SHIFT | 2025-12-14 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
21 | Create SIP flow | Cognigy | Not Started | Red | 2025-12-30 | 2025-12-08 | -22 | PROPORTIONAL SHIFT | 2025-12-14 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
22 | IGT Staging Dependencies Complete | IGT | Not Started | Yellow | 2025-12-23 | 2025-12-08 | 0 | PROPORTIONAL SHIFT | 2025-12-14
23 | Configure 800 number for SIP REFER for CSG Lookup | IGT | Not Started | Red | 2025-12-23 | 2025-12-08 | -15 | PROPORTIONAL SHIFT | 2025-12-14
24 | Set up SIP trunks via NICE CXone | IGT | Not Started | Red | 2025-12-23 | 2025-12-08 | -15 | PROPORTIONAL SHIFT | 2025-12-14
25 | Configure the Signal API | IGT | Not Started | Red | 2025-12-23 | 2025-12-08 | -15 | PROPORTIONAL SHIFT | 2025-12-14
26 | Complete queue mapping | IGT | Not Started | Red | 2025-12-23 | 2025-12-08 | -15 | PROPORTIONAL SHIFT | 2025-12-14
27 | Provision 8 DID test numbers | IGT | Not Started | Red | 2025-12-23 | 2025-12-08 | -15 | PROPORTIONAL SHIFT | 2025-12-14
28 | FPS Development - Knowledgebase | FPS | In Progress | Yellow | 2025-12-11 | 2025-12-08 | 0 | PROPORTIONAL SHIFT | 2025-12-14
29 | Validate the KnowledgeOwl API | FPS | Complete | Green | 2025-12-11 | 2025-12-08 | -3 | PROPORTIONAL SHIFT | 2025-12-14
30 | Optimize FAQ lookup specifically for voice interac | FPS | Complete | Green | 2025-12-11 | 2025-12-08 | -3 | PROPORTIONAL SHIFT | 2025-12-14
31 | Implement fallback logic for unanswered or unclear | FPS | Complete | Green | 2025-12-11 | 2025-12-08 | -3 | PROPORTIONAL SHIFT | 2025-12-14
32 | Tune LLM responses for accuracy and clarity | FPS | In Progress | Yellow | 2025-12-11 | 2025-12-08 | -3 | PROPORTIONAL SHIFT | 2025-12-14
33 | Frontier Production Dependencies Complete | Frontier | In Progress | Green | 2025-12-18 | 2025-12-08 | 0 | PROPORTIONAL SHIFT | 2025-12-14
34 | Secure Architecture Review Board (ARB) approval | Frontier | In Progress | Green | 2025-12-18 | 2025-12-08 | 0 | PROPORTIONAL SHIFT | 2025-12-14
35 | Validate Production KnowledgeOwl APIs | Frontier | Complete | Green | 2025-12-08 | 2025-12-08 | 0 | PROPORTIONAL SHIFT | 2025-12-14
36 | FPS Development - Partner Integrations | FPS | Not Started | Green | 2026-01-07 | 2025-12-12 | 0 | PROPORTIONAL SHIFT | 2025-12-18
37 | Implement required partner API integrations | FPS | Not Started | Red | 2026-01-07 | 2025-12-12 | -26 | PROPORTIONAL SHIFT | 2025-12-18 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
38 | Set up the necessary data exchange endpoints | FPS | Not Started | Red | 2026-01-07 | 2025-12-12 | -26 | PROPORTIONAL SHIFT | 2025-12-18 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
39 | QA & Testing Phase |  | Not Started | Yellow | 2026-01-21 | 2025-12-19 | 0.11 | PROPORTIONAL SHIFT | 2025-12-25 |  |  | COMPRESS 8d | Currently 8 days past target
40 | FPS QA Testing | FPS | Not Started | Green | 2026-01-06 | 2025-12-12 | 0 | PROPORTIONAL SHIFT | 2025-12-18 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
41 | Execute the full end-to-end Agentic Voice test pla | FPS | Not Started | Red | 2026-01-06 | 2025-12-12 | -25 | PROPORTIONAL SHIFT | 2025-12-18 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
42 | Perform all testing within the QA environment | FPS | Not Started | Red | 2026-01-06 | 2025-12-12 | -25 | PROPORTIONAL SHIFT | 2025-12-18 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
43 | CSG Staging Dependencies Complete (Testing) | CSG | Not Started | Yellow | 2025-12-12 | 2025-12-15 | 1 | PROPORTIONAL SHIFT | 2025-12-21
44 | Configure IVR call routing using SIP REFER to IGT | CSG | Not Started | Yellow | 2025-12-12 | 2025-12-15 | 3 | PROPORTIONAL SHIFT | 2025-12-21
45 | Set up the 800 test number for the direct_AI Engli | CSG | Not Started | Yellow | 2025-12-12 | 2025-12-15 | 3 | PROPORTIONAL SHIFT | 2025-12-21
46 | Cognigy Production Dependencies Complete | Cognigy | Not Started | Green | 2026-01-06 | 2025-12-15 | 0 | PROPORTIONAL SHIFT | 2025-12-21 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
47 | Provision the Production 800 number | Cognigy | Not Started | Red | 2026-01-06 | 2025-12-15 | -22 | PROPORTIONAL SHIFT | 2025-12-21 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
48 | Set up SIP trunks to Cognigy | Cognigy | Not Started | Red | 2026-01-06 | 2025-12-15 | -22 | PROPORTIONAL SHIFT | 2025-12-21 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
49 | Configure the Signal API | Cognigy | Not Started | Red | 2026-01-06 | 2025-12-15 | -22 | PROPORTIONAL SHIFT | 2025-12-21 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
50 | Provision 2 DID test numbers | Cognigy | Not Started | Red | 2026-01-06 | 2025-12-15 | -22 | PROPORTIONAL SHIFT | 2025-12-21 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
51 | IGT Production Dependencies Complete | IGT | Not Started | Green | 2026-01-07 | 2025-12-15 | 0 | PROPORTIONAL SHIFT | 2025-12-21 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
52 | Provision the 800 number for production | IGT | Not Started | Red | 2026-01-07 | 2025-12-15 | -23 | PROPORTIONAL SHIFT | 2025-12-21 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
53 | Set up SIP trunks to Cognigy | IGT | Not Started | Red | 2026-01-07 | 2025-12-15 | -23 | PROPORTIONAL SHIFT | 2025-12-21 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
54 | Configure the Signal API | IGT | Not Started | Red | 2026-01-07 | 2025-12-15 | -23 | PROPORTIONAL SHIFT | 2025-12-21 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
55 | Provision 2 DID test numbers | IGT | Not Started | Red | 2026-01-07 | 2025-12-15 | -23 | PROPORTIONAL SHIFT | 2025-12-21 | 24FS +1d | CRITICAL - depends on IGT |  | ¦ Blocked by IGT Row 24
56 | Frontier UAT Testing | Frontier | Not Started | Green | 2026-01-19 | 2025-12-19 | 0 | PROPORTIONAL SHIFT | 2025-12-25 | 40FS +1d |  | COMPRESS 6d | Currently 6 days past target
57 | Execute the full end-to-end Agentic Voice test pla | Frontier | Not Started | Red | 2026-01-19 | 2025-12-19 | -31 | PROPORTIONAL SHIFT | 2025-12-25 | 40FS +1d |  | COMPRESS 6d | Currently 6 days past target
58 | Perform all testing within the UAT environment | Frontier | Not Started | Red | 2026-01-19 | 2025-12-19 | -31 | PROPORTIONAL SHIFT | 2025-12-25 | 40FS +1d |  | COMPRESS 6d | Currently 6 days past target
59 | CSG Production Dependencies Complete (UAT Approval | CSG | In Progress | Green | 2025-12-19 | 2025-12-17 | 0 | PROPORTIONAL SHIFT | 2025-12-23
60 | Configure Production IVR call routing using SIP RE | CSG | In Progress | Yellow | 2025-12-19 | 2025-12-17 | -2 | PROPORTIONAL SHIFT | 2025-12-23
61 | Set the routing percentage for “Unknown” call type | CSG | In Progress | Yellow | 2025-12-19 | 2025-12-17 | -2 | PROPORTIONAL SHIFT | 2025-12-23
62 | Frontier UAT Approval | Frontier | Not Started | Green | 2026-01-21 | 2025-12-19 | 0 | PROPORTIONAL SHIFT | 2025-12-25 | 56FS +1d |  | COMPRESS 8d | Currently 8 days past target
63 | Obtain formal UAT sign-off | Frontier | Not Started | Red | 2026-01-21 | 2025-12-19 | -33 | PROPORTIONAL SHIFT | 2025-12-25 | 56FS +1d |  | COMPRESS 8d | Currently 8 days past target
64 | Production Deployment |  | Not Started | Green | 2026-01-30 | 2026-01-07 | 0 | UPDATE TO JAN 13 | 2026-01-13 | 34FS |  | COMPRESS 17d | Currently 17 days past target
65 | Frontier Production Dependencies Complete | Frontier | In Progress | Green | 2026-01-01 | 2026-01-05 | 0 | PROPORTIONAL SHIFT | 2026-01-11 | 34FS
66 | Provision Production Azure AI Speech STT keys | Frontier | In Progress | Red | 2026-01-01 | 2026-01-05 | -30 | PROPORTIONAL SHIFT | 2026-01-11 | 34FS
67 | Provision Production Azure AI Speech TTS keys | Frontier | In Progress | Red | 2026-01-01 | 2026-01-05 | -30 | PROPORTIONAL SHIFT | 2026-01-11 | 34FS
68 | Set up Production OpenAI LLM credentials | Frontier | Not Started | Red | 2026-01-01 | 2026-01-05 | -30 | PROPORTIONAL SHIFT | 2026-01-11 | 34FS
69 | Frontier Production Go-Live Approval (CAB) | Frontier | Not Started | Green | 2026-01-28 | 2026-01-06 | 0 | PROPORTIONAL SHIFT | 2026-01-12 | 62FS +1d |  | COMPRESS 15d | Currently 15 days past target
70 | Present the deployment plan to the Change Advisory | Frontier | Not Started | Red | 2026-01-28 | 2026-01-06 | -22 | PROPORTIONAL SHIFT | 2026-01-12 | 62FS +1d |  | COMPRESS 15d | Currently 15 days past target
71 | Secure final approval for the Production Go-Live | Frontier | Not Started | Red | 2026-01-28 | 2026-01-06 | -22 | PROPORTIONAL SHIFT | 2026-01-12 | 62FS +1d |  | COMPRESS 15d | Currently 15 days past target
72 | FPS Production Deployment | FPS | Not Started | Green | 2026-01-30 | 2026-01-07 | 0 | UPDATE TO JAN 13 | 2026-01-13 | 69FS +1d |  | COMPRESS 17d | Currently 17 days past target
73 | Deploy the solution to Production | FPS | Not Started | Red | 2026-01-30 | 2026-01-07 | -23 | UPDATE TO JAN 13 | 2026-01-13 | 69FS +1d |  | COMPRESS 17d | Currently 17 days past target
74 | Perform sanity testing to confirm core functionali | FPS | Not Started | Red | 2026-01-30 | 2026-01-07 | -23 | UPDATE TO JAN 13 | 2026-01-13 | 69FS +1d |  | COMPRESS 17d | Currently 17 days past target
75 | Initiate post-launch monitoring to ensure stabilit | FPS | Not Started | Red | 2026-01-30 | 2026-01-07 | -23 | UPDATE TO JAN 13 | 2026-01-13 | 69FS +1d |  | COMPRESS 17d | Currently 17 days past target

## Summary
PHASE 2 AGENTIC VOICE - SCHEDULE CORRECTION PLAN
Generated: | 2025-12-09 17:19:12
TARGET GO-LIVE: | 2026-01-13
CURRENT PROJECTION: | 2026-01-30
DAYS TO COMPRESS: | 17 days
CRITICAL PATH:
1. IGT Row 24 (SIP Trunks) | Dec 23 - BLOCKER
2. FPS Row 40 (QA Testing) | Jan 6
3. Frontier Row 56 (UAT) | Jan 19
4. Frontier Row 62 (UAT Approval) | Jan 21
5. Frontier Row 69 (CAB) | Jan 28
6. FPS Row 72 (Production Deploy) | Jan 30
IMMEDIATE ACTIONS:
1. Update all baselines | Shift +6 days (Jan 7 → Jan 13)
2. Escalate IGT dependency | Can they complete Dec 16?
3. Review Row 24 dependencies | Can any run in parallel?
4. Compress UAT window | 8 days → 5 days?
5. Compress CAB window | 4 days → 2 days?
TASKS OVER TARGET: | 14 tasks
BASELINE UPDATES NEEDED: | 75 tasks
PREDECESSOR REVIEWS: | 20 tasks